## LynxMasters
Task Name | Duration | Start | Finish | Assigned To
Week 1
Proposal | 1d | 2018-03-26 | 2018-03-26 | Ian, Jameson, Tyler, Nick
Status Report | 1d | 2018-03-30 | 2018-03-30 | Ian, Jameson, Tyler, Nick
Gantt Chart | 6d | 2018-03-26 | 2018-04-02 | Ian, Jameson
Week 2
Start Wiki and Docs |  | 2018-04-02 | 2018-04-08
Use Cases | 6d | 2018-04-02 | 2018-04-09 | Nick, Jameson
UI Prototypes | 6d | 2018-04-02 | 2018-04-09 | Tyler, Ian
Status Report | 1d | 2018-04-06 | 2018-04-06 | Ian, Jameson, Nick, Tyler
Week 3
Update UI Prototypes | 5d | 2018-04-09 | 2018-04-13 | Tyler, Ian, Jameson, Nick
Update Use Cases | 5d | 2018-04-09 | 2018-04-13 | Nick, Jameson, Tyler, Ian
Team Agreement | 5d | 2018-04-09 | 2018-04-13 | Ian, Nick, Jameson, Tyler
Status Report | 1d | 2018-04-13 | 2018-04-13 | Ian, Jameson, Tyler, Nick
Week 4
Database Diagrams | 5d | 2018-04-16 | 2018-04-20 | Ian, Jameson
Status Report | 1d | 2018-04-20 | 2018-04-20 | Ian, Jameson, Tyler, Nick
Week 5
Activity Diagrams | 5d | 2018-04-21 | 2018-04-26 | Tyler, Ian, Nick, Jameson
Update Project Components | 5d | 2018-04-22 | 2018-04-26 | Jameson, Tyler, Nick, Ian
Status Report | 1d | 2018-04-20 | 2018-04-20 | Ian, Jameson, Tyler, Nick
Week 6
Class Diagrams | 6d | 2018-04-21 | 2018-04-27 | Tyler, Nick
Status Report | 1d | 2018-04-27 | 2018-04-27 | Ian, Jameson, Tyler, Nick
Week 7
Sequence Diagrams | 6d | 2018-04-28 | 2018-05-04 | Tyler, Nick, Jameson, Ian
Status Report | 1d | 2018-05-04 | 2018-05-04 | Ian, Jameson, Tyler, Nick
Week 8
Update Gantt Chart | 5d | 2018-05-07 | 2018-05-11 | Ian, Tyler, Jameson, Nick
Status Report | 1d | 2018-05-11 | 2018-05-11 | Ian, Jameson, Tyler, Nick
Week 9
Prepare for Presentation | 6d | 2018-05-12 | 2018-05-18 | Ian, Nick, Tyler, Jameson
Update Wiki | 5d | 2018-05-14 | 2018-05-18 | Ian, Jameson, Nick, Tyler
Status Report | 1d | 2018-05-18 | 2018-05-18 | Ian, Jameson, Tyler, Nick
Week 10
Final Presentations | 1d | 2018-05-21 | 2018-05-21 | Ian, Tyler, Jameson, Nick